## Hours
	STUDENT 1
WEEK #	Dissertation	Project	Weekly
January	Hours worked	Hours worked	Total
4
5	0	10	10
February
6	0	16	16			Week 5, 6 are estimates. Didn't know I was supposed log my time
7	1	0	1
8	6		6
9			0
sub-total	7	26	33
March
10			0
11			0
12			0
13			0
14			0
sub-total	0	0	0
April
15			0
16			0
17			0
18			0
sub-total	0	0	0
May
19			0
20			0
21			0
22			0
sub-total	0	0	0
June
23			0
24			0
25			0
sub-total	0	0	0
TOTALS	7	26	33

## Project
	Project				Dissertation
WEEK #	ACTIVITIES	Comments		WEEK #	ACTIVITIES	Comments
January				January
4	Initiate Project. (Specification, research technologies etc)			4
5	Set up the developing environment			5
February				February
6	Create a GUI first screen			6
7		Meeting Hugh Melvin		7	Write Background, time table
8	Create general GUI screens for statistics, select charger, conf. charger, settings	Meeting Hugh Melvin		8	Draft Chapter Two	Meeting Donald Ross
9	Configure a generic connection to a database			9	Deliver Chapter Two, Background
sub-total				sub-total
March				March
10	Configure a generic connection to a database	Meeting Hugh Melvin		10		Meeting Donald Ross
11	Meet with the other group doing phonegap	Meeting H.M. 12/3 15:00		11
12				12	Write implementation, Draft Chapter Three
13				13	Deliver Chapter Three, Experiment / Implementation	Meeting Donald Ross
14				14
sub-total				sub-total
April				April
15				15	Write Evaluation, Draft Chapter Four	Meeting Donald Ross
16				16	Deliver Chapter Four, Results / Evaluation
17				17		Meeting Donald Ross
18				18
sub-total				sub-total
May				May
19				19		Meeting Donald Ross
20				20	Deliver Chapter One, Abstract
21				21	Final version of the report	2014-05-23
22				22	Read dissertation
sub-total				sub-total
June				June
23				23	Defend dissertation
24				24
25				25

## Dissertation
WEEK #	ACTIVITIES
January
4
5
February
6
7	Write Background, time table	Meeting Hugh Melvin, Donald Ross
8		Meeting Hugh Melvin
9	Deliver Chapter Two, Background
sub-total
March
10
11
12	Write implementation
13	Deliver Chapter Three, Experiment / Implementation
14
sub-total
April
15	Write Evalution
16	Deliver Chapter Four, Results / Evaluation
17
18
sub-total
May
19
20	Deliver Chapter One, Abstract
21	Final version of the report	2014-05-23
22	Read dissertation
sub-total
June
23	Defend dissertation
24
25